## Sprint-4.0 Retrospection
Project Name: Team 7- Seat Booking App
Sprint - 4.0 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | Everyone followed the sprint backlog accordingly | Iteration backlog is not updated before standup meeting | Team Members should update iteration backlog before standup meeting |  | Team
2 | Team co-ordination is excellent
3 | Unplanned tasks were few
4 | Conducted Stand-up meeting everyday
5 | Complete research and exploring on their task was done by each person | limited resources for reference hence it took long time for exploration | Team memebers must be more quick in finding the correct solution and ideas |  | Team