## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks | Priority
[7 empty] | 0 | 1 | 2
[7 empty] | 63 | 0 | 0
Application Management / Administration
P1
1 | REQ2 | User Login |  | Release-1 | P2 | Not Started | 17 |  |  |  | P2
2 | REQ3 | Admin Dashboard |  | Release-1 | P3 | Not Started | 15 |  |  |  | P3
3 | REQ4 | Employee Home Page |  | Release-1 | P4 | Not Started | 18 |  |  |  | P1
4 | REQ5 | Profile Info Page |  | Release-1 | P5 | Not Started | 13 |  |  |  | P1
5 | REQ6 | Booking a seat daily/weekly basis |  | Release-1 | P6 | Not Started
6 | REQ7 | Booking a seat in a particular floor |  | Release-2 | P7 | Not Started
8 | REQ9 | Admin approving booking |  | Release-2 | P9 | Not Started
9 | REQ10 | Generating weekly/monthly reports |  | Release-2 | P10 | Not Started

## Burndown
Iteration | 0 | 2
Remaining | 63 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release