## Sprint-4.0 Retrospection
Project Name: XXXXX
Sprint - 2.0 |  | Date: 07-Oct-2022
# | +ve | r | Action Item | Target Date | Responsible
1 | Most of the planned tasks were completed | Due to less time the functionalities could not be enhanced | Have to in advance look for best aproach |  | Team
2 | Team co-ordination is excellent
3 | Unplanned tasks are completed
4 | The time estimation was better than previous sprint
5 | Sloved the errors diligently | Consumed extra time | Should try solving it more quickly |  | Team
6 | Storing booked info in node is working | Retrieving the stored data from the node | Since the methedology is not working we shifted to Json
7 | Finding the best alternative to work